## Project Planning
Conference Planning
ACTIVITY | START | IN PROGRESS | DURATION | COMPLETED | % COMPLETE | PERIODS (unit: week)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task 1: conference content
Possible topics collection | 1 | 0 | 1 | 1 | 100% | bar: PERIODS (unit: week) 1
Data/ Reference overview | 1 | 0 | 2 | 1 | 100% | bar: PERIODS (unit: week) 1 to PERIODS (unit: week) 2
Possible topics discussion | 2 | 0 | 1 | 1 | 100% | bar: PERIODS (unit: week) 2
Task 2: Conference schedule
Conference content | 1 | 0 | 3 | 1 | 100% | bar: PERIODS (unit: week) 1 to PERIODS (unit: week) 3
Preparation (date, location,etc) | 3 | 3 | 4 | 0 | 75% | bar: PERIODS (unit: week) 3 to PERIODS (unit: week) 6
Promotion | 6 | 4 | 6 | 0 | 66.6% | bar: PERIODS (unit: week) 6 to PERIODS (unit: week) 11
Draft revision | 4 | 5 | 7 | 0 | 62.5% | bar: PERIODS (unit: week) 4 to PERIODS (unit: week) 10
Practice and rehearsal | 8 | 1 | 4 | 0 | 20% | bar: PERIODS (unit: week) 8 to PERIODS (unit: week) 11
Feedback collection and summary | 11 | 0 | 3 | 0 | 0% | bar: PERIODS (unit: week) 11 to PERIODS (unit: week) 13
Task 3: Feedback summary
Feedback form | 11 | 0 | 1 | 0 | 0% | bar: PERIODS (unit: week) 11
Feedback form collection | 12 | 0 | 2 | 0 | 0% | bar: PERIODS (unit: week) 12 to PERIODS (unit: week) 13
Result overview and summary | 13 | 0 | 1 | 0 | 0% | bar: PERIODS (unit: week) 13